## Sheet1
Ticket Number | Ticket Creator | Subject | Customer Name | Ticket Department | Status | Ticket Owner | Ticket Priority | Ticket Aging | Start Date | Required Date | Estimate Resolution Date | Description
IT-2026-0101 | Sanket Tambe | QAD ERP Session crash during Month-End closing report generation | United Tyrekrafts Plant 1 | ERP Support | Work in Progress | Sandeep Yadav | Critical | 4 | 2026-09-24 | 2026-09-26 | 2026-09-30 | Finance department reporting unhandled memory exception when exporting batch GL trial balances. Investigating database lock on table gl_hist.
IT-2026-0104 | Rohan Desai | VPN Gateway authentication timeout for remote plant managers | Corporate IT | IT Infrastructure | Work in Progress | Rajesh Kumar | High | 6 | 2026-09-22 | 2026-09-25 | 2026-09-29 | Radius server connection drops during peak afternoon hours. Checking packet loss on primary ISP link.
IT-2026-0108 | Pooja Nair | Barcode scanner connectivity failure on Tyre Curing Line 3 | Plant Operations Pune | Plant IT Operations | Work in Progress | Sneha Patel | High | 8 | 2026-09-20 | 2026-09-23 | 2026-09-30 | Wireless hand terminal disconnects from AP-04 every 20 minutes. Re-configuring roaming thresholds.
IT-2026-0112 | Vikram Malhotra | Slow query performance on Dispatch & Logistics daily summary | Supply Chain Logistics | Database Admin | Work in Progress | Amit Sharma | Medium | 11 | 2026-09-17 | 2026-09-22 | 2026-09-30 | Query takes 4.5 minutes to load 15k rows. Index optimization and partition maintenance in progress.
IT-2026-0115 | Anjali Joshi | Procurement Purchase Order approval email notification delay | Purchasing Dept | ERP Support | Work in Progress | Sandeep Yadav | Medium | 14 | 2026-09-14 | 2026-09-20 | 2026-09-30 | SMTP relay queue backlog observed during automated workflow trigger for POs exceeding threshold limit.
IT-2026-0118 | Manish Tiwari | Automated GST e-Way Bill API integration enhancement | Finance & Taxation | Development | Under Development | Amit Sharma | High | 16 | 2026-09-12 | 2026-09-28 | 2026-10-05 | Building automated payload validation and error handling for government GST portal schema version 1.04 update.
IT-2026-0121 | Sanket Tambe | Custom QC inspection mobile web form for Tyre Tread testing | Quality Assurance | Development | Under Development | Priya Verma | Medium | 19 | 2026-09-09 | 2026-09-25 | 2026-10-02 | Designing responsive tablet input interface with mandatory photo upload and tolerance validation limits.
IT-2026-0125 | Rohan Desai | Inventory Batch Traceability module for Raw Rubber compounds | Warehouse & Materials | Development | Under Development | Sandeep Yadav | High | 22 | 2026-09-06 | 2026-09-26 | 2026-10-10 | Implementing FIFO lot allocation and expiry tracking backend stored procedures in ERP core.
IT-2026-0128 | Vikram Malhotra | Automated Daily Attendance SMS/Email Alert for shift supervisors | HR Department | Development | Under Development | Priya Verma | Low | 25 | 2026-09-03 | 2026-09-20 | 2026-10-01 | Cron script scheduled to aggregate biometric machine logs and fire morning shift exception summary.
IT-2026-0130 | Sanket Tambe | Request for SAP Sub-ledger access and Cost Center 402 permissions | Accounts Dept | ERP Support | Awaiting User Info | Sandeep Yadav | High | 12 | 2026-09-16 | 2026-09-19 | 2026-09-28 | Need signed approval form from department head Mr. Joshi before granting modification rights to ledger.
IT-2026-0133 | Anjali Joshi | Vendor master bank details update rejection error | Accounts Payable | ERP Support | Awaiting User Info | Rajesh Kumar | Medium | 15 | 2026-09-13 | 2026-09-18 | 2026-09-27 | Waiting for verified cancelled cheque copy and vendor GST registration certificate from user.
IT-2026-0137 | Pooja Nair | Replacement of damaged weighing scale serial communication cable | Finished Goods Store | IT Infrastructure | Awaiting User Info | Sneha Patel | Medium | 18 | 2026-09-10 | 2026-09-15 | 2026-09-25 | Need exact hardware model and serial pin configuration (RS232 DB9 vs DB25) from store in-charge.
IT-2026-0140 | Manish Tiwari | Discrepancy in Q3 Sales commission rebate percentage calculation | Commercial Sales | ERP Support | Awaiting User Info | Sandeep Yadav | High | 24 | 2026-09-04 | 2026-09-12 | 2026-09-29 | Requested policy amendment circular number and approved tier formula from VP Sales.
IT-2026-0145 | Rohan Desai | Server Room UPS Battery replacement and thermal cooling overhaul | Infrastructure & Plant Maint | IT Infrastructure | Hold | Rajesh Kumar | High | 35 | 2026-08-24 | 2026-09-10 | 2026-10-15 | Awaiting capital expenditure budget approval from executive committee for Eaton 40kVA battery banks.
IT-2026-0148 | Vikram Malhotra | License renewal for 3D CAD Mold Design software | R&D Tyre Design | IT Infrastructure | Hold | Sneha Patel | Medium | 40 | 2026-08-19 | 2026-09-05 | 2026-10-20 | Vendor quote review in progress by commercial audit team. Negotiations on concurrent license counts.
IT-2026-0151 | Sanket Tambe | New user desktop onboarding for Quality Inspector - Plant 2 | Quality Assurance | IT Infrastructure | Open | Sneha Patel | Medium | 2 | 2026-09-27 | 2026-09-30 | 2026-10-01 | Standard Windows 11 installation with ERP client, antivirus, and local network printer mapping.
IT-2026-0154 | Pooja Nair | Production work order print misalignment on Line 1 Dot Matrix | Production Line 1 | Plant IT Operations | Open | Rajesh Kumar | High | 3 | 2026-09-26 | 2026-09-28 | 2026-09-30 | Top margin offset shifted by 1.5 inches after continuous stationery paper roll change.
IT-2026-0158 | Manish Tiwari | Reset locked active directory account for regional sales executive | North Zone Sales | IT Infrastructure | Open | Sandeep Yadav | Low | 1 | 2026-09-28 | 2026-09-29 | 2026-09-29 | User entered wrong password on mobile Outlook client repeatedly. Account locked out.
IT-2026-0162 | Anjali Joshi | Quarterly physical inventory stock audit reconciliation mismatch | Finance & Audit | ERP Support | Pending | Sandeep Yadav | High | 21 | 2026-09-07 | 2026-09-18 | 2026-10-03 | Pending physical count sign-off from external auditors for Unitread Nashik warehouse.
IT-2026-0166 | Rohan Desai | Fiber link splicing approval from highway authority for Plant 3 expansion | Network Projects | IT Infrastructure | Pending | Rajesh Kumar | Medium | 28 | 2026-08-31 | 2026-09-15 | 2026-10-12 | Right of way clearance permission pending with state road development corporation.
IT-2026-0171 | Sanket Tambe | Thermal barcode label printer ribbon replacement in Dispatch | Dispatch Store | Plant IT Operations | Closed | Sneha Patel | Medium | 7 | 2026-09-18 | 2026-09-21 | 2026-09-22 | Replaced wax-resin ribbon and cleaned printhead with isopropyl alcohol. Test print verified.
IT-2026-0175 | Pooja Nair | Email forwarding rule configured for retired store supervisor | Human Resources | IT Infrastructure | Closed | Rajesh Kumar | Low | 5 | 2026-09-21 | 2026-09-24 | 2026-09-24 | Configured M365 auto-forwarding to current store in-charge as per HR exit checklist.
IT-2026-0179 | Vikram Malhotra | Monthly database vacuum and index rebuild on production cluster | Internal IT Ops | Database Admin | Closed | Amit Sharma | High | 3 | 2026-09-24 | 2026-09-26 | 2026-09-25 | Completed scheduled maintenance window on Sunday night. Freed 42GB unindexed space.
IT-2026-0182 | Anjali Joshi | Credit memo authorization workflow issue for returned tread rubber | Customer Billing | ERP Support | Closed | Sandeep Yadav | Critical | 4 | 2026-09-23 | 2026-09-25 | 2026-09-26 | Resolved table lock on credit note verification queue. Processed 14 held memos.