## Sheet1
Ticket Number | Ticket Creator | Subject | Customer Name | Ticket Department | Status | Ticket Owner | Ticket Priority | Ticket Aging | Start Date | Required Date | Estimate Resolution Date | Description
IT-2026-0101 | Sanket Tambe | QAD ERP Session crash during Month-End closing report generation | United Tyrekrafts Plant 1 | ERP Support | Work in Progress | Sandeep Yadav | Critical | 4 | 2026-09-24 | 2026-09-26 | 2026-09-30 | Finance department reporting unhandled memory exception when exporting batch GL trial balances. Investigating database lock on table gl_hist.
IT-2026-0104 | Rohan Desai | VPN Gateway authentication timeout for remote plant managers | Corporate IT | IT Infrastructure | Work in Progress | Rajesh Kumar | High | 6 | 2026-09-22 | 2026-09-25 | 2026-09-29 | Radius server connection drops during peak afternoon hours. Checking packet loss on primary ISP link.
IT-2026-0108 | Pooja Nair | Barcode scanner connectivity failure on Tyre Curing Line 3 | Plant Operations Pune | Plant IT Operations | Work in Progress | Sneha Patel | High | 8 | 2026-09-20 | 2026-09-23 | 2026-09-30 | Wireless hand terminal disconnects from AP-04 every 20 minutes. Re-configuring roaming thresholds.
IT-2026-0112 | Vikram Malhotra | Slow query performance on Dispatch & Logistics daily summary | Supply Chain Logistics | Database Admin | Work in Progress | Amit Sharma | Medium | 11 | 2026-09-17 | 2026-09-22 | 2026-09-30 | Query takes 4.5 minutes to load 15k rows. Index optimization and partition maintenance in progress.
IT-2026-0115 | Anjali Joshi | Procurement Purchase Order approval email notification delay | Purchasing Dept | ERP Support | Work in Progress | Sandeep Yadav | Medium | 14 | 2026-09-14 | 2026-09-20 | 2026-09-30 | SMTP relay queue backlog observed during automated workflow trigger for POs exceeding threshold limit.